## Engagements
id | Employee Name | Site Engaged | Starting Date | End Date | Duration (Days) | status
ENG-00001 | Dhirendra Kumar | Mewa Khola | 2026-01-01 |  | 43 | Active
ENG-00002 | Nobeshor Yadav | Seti khola | 2025-12-15 |  | 60 | Active
ENG-00003 | Ganesh Budha | Thulo Khola | 2025-12-16 |  | 59 | Active
ENG-00004 | Shakti Bhushan | Shyarpu khola | 2025-12-17 |  | 58 | Active
ENG-00005 | Biraj Sharma | Seti khola | 2024-12-12 |  | 428 | Active
ENG-00006 | Akshaya Kumar | Seti khola | 2026-02-08 |  | 5 | Active
ENG-00007 | Ram Adhikari | Mewa Khola | 2025-09-08 |  | 158 | Active
ENG-00008 | Sunil Halder | Mewa Khola | 2025-09-09 |  | 157 | Active
ENG-00009 | Sunil Giri | kathmandu Office | 2025-09-10 |  | 156 | Active
ENG-00010 | Ayush Karki | kathmandu Office | 2025-09-11 |  | 155 | Active
ENG-00011 | Dedej Kasem | Thulo Khola | 2025-09-12 |  | 154 | Active
ENG-00012 | Sergio Feitosa | Seti khola | 2025-09-13 |  | 153 | Active
ENG-00013 | Tobia Walpoth | Italy | 2025-09-14 |  | 152 | Active
ENG-00014 | Akshaya Kumar | Mewa Khola | 2025-10-24 | 45974 | 20 | Completed
ENG-00015 | Akshaya Kumar | Chepe Khola | 2025-11-14 | 45996 | 21 | Completed
ENG-00016 | Akshaya Kumar | Seti khola | 2025-12-06 | 46020 | 23 | Completed
ENG-00017 | Akshaya Kumar | Upper Khudi | 2025-12-30 | 46060 | 39 | Completed
ENG-00018 | Ram Adhikari | Thulo Khola | 2025-03-05 | 45897 | 176 | Completed
ENG-00019 | Ram Adhikari | ON LEAVE | 2025-08-30 | 45907 | 8 | Completed

## Sites_List
Location | Status
Mewa Khola | Installation
Seti khola | Installation
Shyarpu khola | Installation
Upper Khudi | Installation
Upper Myagdi | Installation
Nyasim Khola | Installation
Upper Myagdi 1 (FR) | Installation
Luja Khola | Installation
Chepe Khola | Installation
Dodhpokhari Chepe | Installation
Sabha Khola B | Installation
Thulo Khola | Installation
kathmandu Office | Installation
Delhi Office | Installation
Italy | Installation
ON LEAVE | Installation

## profiles
id | Employee Name | Designation
EMP-00001 | Dhirendra Kumar | Mechanical Manager
EMP-00002 | Nobeshor Yadav | Electrical Manager
EMP-00003 | Ganesh Budha | Electrician
EMP-00004 | Shakti Bhushan | Electrical Coordinator (Site)
EMP-00005 | Biraj Sharma | Mechanical Engineer
EMP-00006 | Akshaya Kumar | Senior Foreman
EMP-00007 | Ram Adhikari | Site Coordinator
EMP-00008 | Sunil Halder | Welder
EMP-00009 | Sunil Giri | Project site Manager
EMP-00010 | Ayush Karki | Sales Engineer
EMP-00011 | Dedej Kasem | Electrical Engineer
EMP-00012 | Sergio Feitosa | Sr. Mechanical Technician
EMP-00013 | Tobia Walpoth | Automation Engineer
EMP-00014 | pradeep koirala | Manager

## Tools
TOOLS FROM THULO KHOLA
S.N | Item | UoM | Qty | Location | Remarks
1 | TIG Welding Machine | Nos | 4 | seti container
2 | Argon Welding Machine (3 phase) | Nos | 1 | seti container
3 | Hydraulic Aluminium Tap bender Machine | Set | 1 | seti container
4 | Air Compressor Machine | Nos | 1 | seti container
5 | Vacuum Cleaner Machine | Nos | 1 | seti container
6 | Oil Filtration Machine | Nos | 1 | thulo khola
7 | Hydraulic Jack (50 Ton) (10 Ton) – 2 pcs each | Nos | 2 | seti container
8 | Safety Belt | Pcs | 3 | seti container
9 | Cut-off Machine | Nos | 1 | seti container
10 | AG7 Grinding Machine | Nos | 2 | seti container
11 | Electrode Oven Machine | Nos | 1 | seti container
12 | Tabletop Ladles | Nos | 1 | seti container
13 | Air Blower Machine | Nos | 2 | thulo khola
14 | Hot Air Gun | Nos | 2 | seti container
15 | Hammer Drilling (hammer drill) | Nos | 1 | seti container
16 | Torque Wrench 2000 R | Nos | 1 | seti container
17 | Torque Wrench 160 R | Nos | 1 | seti container
18 | Hydraulic Crimping | Nos | 1 | seti container
19 | Chain Block
| 10 Ton | Nos | 1 | seti container
| 6 Ton | Nos | 1 | seti container
| 5 Ton | Nos | 1 | thulo khola
| 3 Ton | Nos |  | thulo khola
20 | Spirit Level
| Small | Nos | 4 | seti container
| Large | Nos | 1 | seti container
| Medium | Nos | 2 | seti container
21 | AG 4 Grinding Machine | Nos | 1 | seti container
22 | Mini Tap Bender Machine | Nos | 1 | seti container
23 | Serial Print Machine | Nos | 1 | seti container
24 | Crane Lifting Belt
| 3 Ton 6 meter | Nos | 2 | seti container
| 3 Ton 4 meter | Nos | 4 | seti container
| 2 Ton 4 meter | Nos | 2 | seti container
| 4 Ton 2 meter | Nos | 1 | seti container
| 1 Ton 1 meter | Nos | 2 | seti container
25 | Wrench | Set | 1 | seti container
26 | Taparia Sockets (Taparia brand socket set) | Set | 2 | seti container
27 | Megger Machine (Megger insulation tester) | Nos | 1 | seti container
28 | Handling Manual Hydraulic Pallet Truck Lifting (capacity 2000kg) | Nos | 1 | seti container
29 | Cordless Impact Wrench | Nos | 2 | seti container
30 | Bench Vise | Nos | 1 | seti container
31 | Hydraulic Air Torque Pump Machine | Set | 1 | seti container
32 | Toptul Tool Set | Set | 2 | seti container
33 | Allen Key Bits Toptul | Set | 1 | seti container
34 | Conductors Cutter Machine | Set | 1 | seti container
35 | Digital Multimeter | Nos | 1 | thulo khola
36 | Clamp Meter | Nos | 1 | thulo khola
37 | Digital Tachometer | Set | 1 | seti container
38 | Master Level | Nos | 1 | seti container
39 | Digital Leakage Machine | Set | 1 | seti container
40 | Digital Vernier Caliper | Nos | 1 | seti container
41 | Analog Vernier Caliper | Nos | 1 | seti container

## Seti_Updated
ID | Task Mode | % Complete | Task Name | Duration (days) | Start | Finish | Predecessors
1 |  | 3% | Upper Myagdi-1 (HPP) | 851 | 2025-07-17 | 2027-11-15
2 |  | 0% | Contract milestones as per Contract | 743 | 2025-07-17 | 2027-07-30
3 |  | 100% | Receiving Letter of Award | 0 | 2025-07-17 | 2025-07-17
4 |  | 100% | Receiving Token amount money | 0 | 2025-08-01 | 2025-08-01
5 |  | 100% | Submission of Preliminary Powerhouse drawing & | 0 | 2025-09-15 | 2025-09-15
6 |  | 100% | Official Signing of contract | 0 | 2025-09-08 | 2025-09-08
7 |  | 100% | Opening of Letter of Credit (LC) | 0 | 2025-12-05 | 2025-12-05
8 |  | 50% | Submission of PH Layout / SLD / Transformer Layout / | 0 | 2025-12-19 | 2025-12-19 | 7FS+14 days
9 |  | 100% | Dispatch of earthing materials | 0 | 2026-12-17 | 2026-12-17 | 7FS+42 days
10 |  | 0% | Dispatch of Crane | 0 | 2026-08-20 | 2026-08-20 | 7FS+182 days
11 |  | 0% | Submission of documents as per list | 0 | 2027-01-28 | 2027-01-28 | 7FS+259 days
12 |  | 0% | Dispatch of Generators and Transformers from India | 0 | 2027-03-25 | 2027-03-25 | 7FS+406 days
13 |  | 0% | Goods reached at Site (latest) | 0 | 2027-02-26 | 2027-02-26 | 7FS+448 days
14 |  | 0% | Dispatch of Switchyard equipment | 0 | 2027-07-15 | 2027-07-15 | 7FS+532 days
15 |  | 0% | Start of Erection works | 0 | 2027-07-29 | 2027-07-29 | 7FS+448 days
16 |  | 0% | Commissioning of Power plant | 0 | 2027-07-29 | 2027-07-29 | 7FS+588 days
17 |  | 0% | Final Commissioning | 0 | 2027-07-30 | 2027-07-30 | 7FS+602 days
18 |  | 0% | Taking Over Certificate | 0 | 2027-07-30 | 2027-07-30 | 7FS+602 days
19 |  | 3% | Troyer Hydro Scope | 851 | 2025-07-17 | 2027-11-15
20 |  | 99% | Design & Drawings | 87.56 | 2026-02-28 | 2025-12-03
21 |  | 100% | Powerhouse GA & Layout Drawings | 60 | 2025-12-05 | 2026-02-03
22 |  | 100% | Earthing Design & Drawings | 57 | 2025-12-05 | 2026-01-31
23 |  | 100% | SLD Approval | 60 | 2026-01-31 | 2025-12-03
24 |  | 0% | Turbine Casing/Draft Tube drawings(From ITA) | 0 | 2026-02-28 | 2026-02-28
25 |  | 0% | Procurement and Supply From Troyer Hydro | 681.44 | 2025-07-17 | 2027-05-29
26 |  | 0% | Powerhouse | 420 | 2025-12-09 | 2027-02-01
27 |  | 6% | Earthing Works | 53 | 2026-02-20 | 2025-12-29
28 |  | 100% | Dispatch of earthing Material | 1 | 2025-12-30 | 2025-12-29
29 |  | 100% | Transport & Custom Clearence (Nepal) | 1 | 2026-01-20 | 2026-01-21
30 |  | 0% | Laying of earthmat | 30 | 2026-02-20 | 2026-01-21
31 |  | 0% | EOT Crane (60/10 Ton Cap.) | 128.5 | 2026-01-27 | 2026-06-05
32 |  | 100% | Order Finalization | 0 | 2026-01-27 | 2026-01-27
33 |  | 0% | Manufacturing Including Drawings Approval | 107 | 2026-01-27 | 2026-05-14
34 |  | 0% | FAT | 0.5 | 2026-05-14 | 2026-05-15
35 |  | 0% | Transportation & Custom Clearence | 21 | 2026-05-15 | 2026-06-05
36 |  | 0% | Draft-tube | 240 | 2026-03-01 | 2026-10-27
37 |  | 0% | Order Finalization | 0 | 2026-03-01 | 2026-03-01 | 24FS+1 day
38 |  | 0% | Manufacturing | 210 | 2026-03-01 | 2026-09-27
39 |  | 0% | Transportation & Custom Clearence | 30 | 2026-09-27 | 2026-10-27
40 |  | 0% | Spiral Casing | 300 | 2026-03-01 | 2026-12-26
41 |  | 0% | Order Finalization | 0 | 2026-03-01 | 2026-03-01 | 24FS+1 day
42 |  | 0% | Manufacturing | 240 | 2026-03-01 | 2026-10-27
43 |  | 0% | Assembly/Inspection & Testing | 30 | 2026-10-27 | 2026-11-26
44 |  | 0% | Transportation & Custom Clearence | 30 | 2026-11-26 | 2026-12-26
45 |  | 0% | Main Inlet Valve (Butterfly type) | 330 | 2026-12-29 | 2026-02-02
46 |  | 0% | Ordering | 0 | 2026-02-02 | 2026-02-02
47 |  | 0% | Design of Valve | 60 | 2026-04-03 | 2026-02-02
48 |  | 0% | Manufacturing including FAT | 240 | 2026-04-03 | 2026-11-29
49 |  | 0% | Transportation & Custom Clearence | 30 | 2026-11-29 | 2026-12-29
50 |  | 0% | Turbine Components from India | 323 | 2026-02-06 | 2026-12-26
51 |  | 0% | Issuance of PO from Troyer -ITA | 0 | 2026-02-06 | 2026-02-06
52 |  | 0% | Issuance of PO to Supplier | 0 | 2026-02-13 | 2026-02-13 | 51FS+7 days
53 |  | 0% | Bearings | 137 | 2026-02-13 | 2026-06-30
54 |  | 0% | Shafts | 120 | 2026-03-01 | 2026-06-29
55 |  | 0% | Other Misc. Turbine Components | 300 | 2026-03-01 | 2026-12-26
56 |  | 0% | Generator | 390 | 2025-12-09 | 2027-01-02
57 |  | 0% | Order Date | 0 | 2025-12-09 | 2025-12-09
58 |  | 0% | Manufacturing Including Drawings Approval | 330 | 2025-12-09 | 2026-11-03
59 |  | 0% | FAT | 30 | 2026-12-03 | 2026-11-04
60 |  | 0% | Dispatch | 45 | 2026-11-19 | 2027-01-02
61 |  | 0% | Oil Filtration System | 30 | 2027-01-02 | 2027-02-01
62 |  | 0% | Order Finalization | 0 | 2027-01-02 | 2027-01-02 | 60
63 |  | 0% | Supply | 30 | 2027-01-03 | 2027-02-01
64 |  | 0% | Cables & associated Items | 30 | 2027-01-03 | 2027-02-01
65 |  | 0% | Penstock Protection Valve | 290 | 2026-03-31 | 2027-01-15
66 |  | 0% | Ordering | 0 | 2026-03-31 | 2026-03-31
67 |  | 0% | Design of Valve | 60 | 2026-03-31 | 2026-05-30
68 |  | 0% | Manufacturing including FAT | 200 | 2026-05-30 | 2026-12-16
69 |  | 0% | Transportation & Custom Clearence | 30 | 2027-01-15 | 2026-12-16
70 |  | 0% | HOT Crane (20 Ton Cap.) | 353 | 2026-01-27 | 2027-01-15
71 |  | 0% | Order Finalization | 0 | 2026-01-27 | 2026-01-27
72 |  | 0% | Manufacturing Including Drawings Approval | 120 | 2026-01-27 | 2026-05-27
73 |  | 0% | Transportation & Custom Clearence | 30 | 2027-01-15 | 2026-12-16
74 |  | 0% | Switchyard & Switchgear | 622.44 | 2025-07-17 | 2027-03-31
75 |  | 0% | NGT Panels | 120 | 2025-07-17 | 2025-11-14
76 |  | 0% | Power Transformers | 390 | 2025-12-09 | 2027-01-02
77 |  | 100% | Order date | 0 | 2025-12-09 | 2025-12-09
78 |  | 0% | Manufacturing | 330 | 2025-12-09 | 2026-11-03
79 |  | 0% | Testing | 30 | 2026-12-03 | 2026-11-04
80 |  | 0% | Dispatch | 30 | 2026-12-04 | 2027-01-02
81 |  | 0% | Curent Transformers & Voltage Transformers | 427.44 | 2026-01-28 | 2027-03-31
82 |  | 0% | Order Finalization | 0 | 2026-01-28 | 2026-01-28
83 |  | 0% | Manufacturing and Supply to site | 300 | 2026-06-05 | 2027-03-31
84 |  | 0% | Auxillary Transformers/Isolation Transformer | 409 | 2026-02-16 | 2027-03-31
85 |  | 0% | Order Finalization | 0 | 2026-02-16 | 2026-02-16
86 |  | 0% | Manufacturing and Supply to site | 180 | 2026-10-03 | 2027-03-31
87 |  | 0% | Lightening Arresters | 381 | 2026-03-16 | 2027-03-31
88 |  | 0% | Order Finalization | 0 | 2026-03-16 | 2026-03-16
89 |  | 0% | Manufacturing and Supply to site | 60 | 2027-01-31 | 2027-03-31
90 |  | 0% | LAVT Panels | 322 | 2027-01-31 | 2026-03-16
91 |  | 0% | Order Finalization | 0 | 2026-03-16 | 2026-03-16
92 |  | 0% | Manufacturing and Supply to site | 120 | 2026-10-04 | 2027-01-31
93 |  | 0% | Circuit Breakers | 350 | 2027-01-31 | 2026-02-16
94 |  | 0% | Order Finalization | 0 | 2026-02-16 | 2026-02-16
95 |  | 0% | Manufacturing and Supply to site | 180 | 2027-01-31 | 2026-08-05
96 |  | 0% | Disconnecting Switches | 350 | 2027-01-31 | 2026-02-16
97 |  | 0% | Order Finalization | 0 | 2026-02-16 | 2026-02-16
98 |  | 0% | Manufacturing and Supply to site | 180 | 2027-01-31 | 2026-08-05
99 |  | 0% | Protection Relays | 350 | 2027-01-31 | 2026-02-16
100 |  | 0% | Order Finalization | 0 | 2026-02-16 | 2026-02-16
101 |  | 0% | Manufacturing and Supply to site | 210 | 2027-01-31 | 2026-07-06
102 |  | 0% | Switchyard Supporting Steel Structure | 183.44 | 2026-08-01 | 2027-01-31
103 |  | 0% | Order Finalization | 0 | 2026-08-01 | 2026-08-01
104 |  | 0% | Manufacturing and Supply to site | 153 | 2026-09-01 | 2027-01-31
105 |  | 0% | Conductor | 242.44 | 2027-02-28 | 2026-07-01
106 |  | 0% | Order Finalization | 0 | 2026-07-01 | 2026-07-01
107 |  | 0% | Manufacturing and Supply to site | 90 | 2026-12-01 | 2027-02-28
108 |  | 0% | Other Misc. Items | 180 | 2026-12-01 | 2027-05-29
109 |  | 0% | DG Sets | 180 | 2026-12-01 | 2027-05-29
110 |  | 0% | DC UPS Syatems | 90 | 2027-05-29 | 2027-03-01
111 |  | 0% | Illumination System | 60 | 2027-05-29 | 2027-03-31
112 |  | 0% | Fire protection System | 60 | 2027-05-29 | 2027-03-31
113 |  | 0% | Video Surveillance Systems | 60 | 2027-05-29 | 2027-03-31
114 |  | 0% | HVAC Systems | 90 | 2027-05-29 | 2027-03-01
115 |  | 0% | Erection Activities | 528.5 | 2026-06-05 | 2027-11-15
116 |  | 0% | EOT Crane (60/10 Ton Cap.) Installation & | 15 | 2026-06-05 | 2026-06-20
117 |  | 0% | Mechanical Works | 305 | 2026-11-03 | 2027-09-04
118 |  | 0% | Mechanical assembly draft tube MG1 | 14 | 2026-11-03 | 2026-11-17
119 |  | 0% | Mechanical assembly draft tube MG2 | 14 | 2026-11-17 | 2026-12-01
120 |  | 0% | Mechanical assembly draft tube MG3 | 14 | 2026-12-01 | 2026-12-15
121 |  | 0% | Customer concreting draft tubes (5 layers min.) | 15 | 2026-12-15 | 2026-12-30
122 |  | 0% | Mechanical assembly cones + spirals + MIVs + | 21 | 2026-12-30 | 2027-01-20
123 |  | 0% | Mechanical assembly cones + spirals + MIVs + | 21 | 2027-01-20 | 2027-02-10
124 |  | 0% | Mechanical assembly cones + spirals + MIVs + | 21 | 2027-02-10 | 2027-03-03
125 |  | 0% | Customer concreting spirals and MIVs | 15 | 2027-03-18 | 2027-03-03
126 |  | 0% | Mechanical assembly distributors + Shaft Seal + | 35 | 2027-03-18 | 2027-04-22
127 |  | 0% | MMGec1hanical assembly distributors + Shaft Seal + | 35 | 2027-04-22 | 2027-05-27 | 126 Mechanical assembly distributors + Shaft Seal + water and air circuits + bearing + generator axis MG2
128 |  | 0% | MMGec2hanical assembly distributors + Shaft Seal + | 35 | 2027-05-27 | 2027-07-01 | 127 Mechanical assembly distributors + Shaft Seal + water and air circuits + bearing + generator axis MG3
129 |  | 0% | MMGec3hanical assembly generator MG1 | 30 | 2027-04-22 | 2027-05-22 | 126 Mechanical assembly generator MG1
130 |  | 0% | Mechanical assembly generator MG2 | 30 | 2027-05-27 | 2027-06-26
131 |  | 0% | Mechanical assembly generator MG3 | 30 | 2027-07-01 | 2027-07-31
132 |  | 0% | Customer concreting generators anchor bolts | 14 | 2027-07-31 | 2027-08-14
133 |  | 0% | Mech. assembly finalization (piping) MG1 | 7 | 2027-08-14 | 2027-08-21
134 |  | 0% | Mech. assembly finalization (piping) MG2 | 7 | 2027-08-21 | 2027-08-28
135 |  | 0% | Mech. assembly finalization (piping) MG3 | 7 | 2027-08-28 | 2027-09-04
136 |  | 0% | Mechanical assembly PHSS | 112 | 2027-04-17 | 2027-08-07
137 |  | 0% | Mechanical assembly RESS | 112 | 2027-04-17 | 2027-08-07
138 |  | 0% | Electrical installation | 105 | 2027-06-26 | 2027-10-09
139 |  | 0% | Cabletreyworks Control room | 21 | 2027-06-26 | 2027-07-17
140 |  | 0% | Cabletreyworks Machine room | 21 | 2027-07-17 | 2027-08-07
141 |  | 0% | Cabletreyworks PHSS | 14 | 2027-08-07 | 2027-08-21
142 |  | 0% | Cabletreyworks RESS | 14 | 2027-08-07 | 2027-08-21
143 |  | 0% | Laying and Electrical cabling MG1 | 21 | 2027-08-07 | 2027-08-28
144 |  | 0% | Laying and Electrical cabling MG2 | 21 | 2027-08-28 | 2027-09-18
145 |  | 0% | Laying and Electrical cabling MG3 | 21 | 2027-09-18 | 2027-10-09
146 |  | 0% | Electrical cabling PHSS | 14 | 2027-08-21 | 2027-09-04
147 |  | 0% | Electrical cabling RESS | 14 | 2027-08-21 | 2027-09-04
148 |  | 0% | Commissioning | 72 | 2027-09-04 | 2027-11-15
149 |  | 0% | Penstock ready from customer | 0 | 2027-09-04 | 2027-09-04 | 135FF
150 |  | 0% | HV line ready from customer | 0 | 2027-09-04 | 2027-09-04 | 135FF
151 |  | 0% | PPV ready to fill water | 0 | 2027-09-04 | 2027-09-04 | 135FF
152 |  | 0% | Internet ready from customer | 0 | 2027-09-04 | 2027-09-04 | 135FF
153 |  | 0% | Signal testing powerhouse | 14 | 2027-09-04 | 2027-09-18
154 |  | 0% | Dry commissioning powerhouse | 21 | 2027-09-18 | 2027-10-09
155 |  | 0% | Wet commissioning powerhouse | 14 | 2027-10-09 | 2027-10-23
156 |  | 0% | Signal testing PHSS | 14 | 2027-09-04 | 2027-09-18
157 |  | 0% | Dry commissioning PHSS | 14 | 2027-09-18 | 2027-10-02
158 |  | 0% | Signal testing RESS | 14 | 2027-09-04 | 2027-09-18
159 |  | 0% | Dry commissioning RESS | 14 | 2027-09-18 | 2027-10-02
160 |  | 0% | NEA acceptance and parallel operation | 1 | 2027-10-23 | 2027-10-24
161 |  | 0% | Preparation HPP operating manual | 0 | 2027-11-14 | 2027-11-14 | 163FF
162 |  | 0% | Trial period | 21 | 2027-10-24 | 2027-11-14
163 |  | 0% | Provisional Acceptance | 0 | 2027-11-14 | 2027-11-14 | 162
164 |  | 0% | Final Acceptance | 0 | 2027-11-15 | 2027-11-15

## Khudi_Timeline
Task Name / Milestone | Duration (days) | Start Date | Finish Date | Notes / Section | time axis 2026-03-15 to 2026-08-30
KHUDI VP
Unit 1
TURBINE
First stage embedded parts & pipes | 4 | 2026-03-15 | 2026-03-18
Turbine housing parts & pipes | 4 | 2026-03-19 | 2026-03-22
Distributor pipe installation | 6 | 2026-03-23 | 2026-03-28
Distributor pipe concreting | 6 | 2026-03-29 | 2026-04-03
Concreting up to Machine hall | 9 | 2026-04-04 | 2026-04-12
Main inlet valve | 8 | 2026-04-13 | 2026-04-20
Concrete Second stage | 12 | 2026-04-21 | 2026-05-02
Runner Installation | 5 | 2026-08-04 | 2026-08-08
Test prior to handover to commissioning | 2 | 2026-08-09 | 2026-08-10
GENERATOR U1 | 1
GEN and bearing preparation | 7 | 2026-06-03 | 2026-06-09
Main erection | 8 | 2026-06-10 | 2026-06-17
Final erection and allignment check | 6 | 2026-06-18 | 2026-06-23
Foundation Second Stage | 8 | 2026-06-24 | 2026-07-01
Piping | 3 | 2026-07-02 | 2026-07-04
Diagnostics & Monitoring | 4 | 2026-07-05 | 2026-07-08
EPS U1 | 1
Secondary Earthing System | 4 | 2026-07-10 | 2026-07-13
Cable supports & Cable tray | 3 | 2026-07-14 | 2026-07-16
Cabling | 4 | 2026-07-17 | 2026-07-20
Low Voltage AC/DC Distribution and MCC | 3 | 2026-07-21 | 2026-07-23
Excitation System incl. Excitation Transformer | 3 | 2026-07-21 | 2026-07-23
Unit Control and Protection System | 3 | 2026-07-21 | 2026-07-23
Unit 2
TURBINE
First stage embedded parts & pipes | 4 | 2026-04-04 | 2026-04-07
Turbine housing parts & pipes | 4 | 2026-04-08 | 2026-04-11
Distributor pipe installation | 6 | 2026-04-13 | 2026-04-18
Distributor pipe concreting | 6 | 2026-04-20 | 2026-04-25
Concreting up to Machine hall | 9 | 2026-04-27 | 2026-05-05
Main inlet valve | 8 | 2026-05-06 | 2026-05-13
Concrete Second stage | 15 | 2026-05-14 | 2026-05-28
Runner Installation | 5 | 2026-08-04 | 2026-08-08
Test prior to handover to commissioning | 2 | 2026-08-09 | 2026-08-10
GENERATOR U2
GEN and bearing preparation | 7 | 2026-06-24 | 2026-07-01
Main erection | 8 | 2026-07-02 | 2026-07-10
Final erection and allignment check | 6 | 2026-07-10 | 2026-07-16
Foundation Second Stage | 8 | 2026-07-17 | 2026-07-25
Piping | 3 | 2026-07-26 | 2026-07-29
Diagnostics & Monitoring | 4 | 2026-07-30 | 2026-08-03
EPS U2
Secondary Earthing System | 4 | 2026-08-03 | 2026-08-06
Cable supports & Cable tray | 3 | 2026-08-07 | 2026-08-09
Cabling | 4 | 2026-08-10 | 2026-08-13
Low Voltage AC/DC Distribution and MCC | 3 | 2026-08-14 | 2026-08-16
Excitation System incl. Excitation Transformer | 3 | 2026-08-14 | 2026-08-16
Unit Control and Protection System | 3 | 2026-08-14 | 2026-08-16
Common EPS
Earthing System (SY) | 8 | 2026-06-02 | 2026-06-09
132 KV Switchyard Erection of Steel Structures | 24 | 2026-06-12 | 2026-07-05
Equipments (HV / MV / LV) | 20 | 2026-06-26 | 2026-07-15
Installation of Power and Auxilliary Transformer | 5 | 2026-07-18 | 2026-07-22
Cable tray work on control room and switchyard | 14 | 2026-07-23 | 2026-08-05
Control cable laying and termination works from control cabinets to MV panels and SY. Power cable laying and termination works from MV to SY. | 17 | 2026-08-06 | 2026-08-22
Power cable kit preparation and connection from Unit 1 and 2 to MV panels | 5 | 2026-08-23 | 2026-08-27
Installation of DG Set | 2 | 2026-07-18 | 2026-07-19
Cabling & Cable Support System (DG) | 3 | 2026-07-20 | 2026-07-22
Other Systems (Lighting System, Fire Fighting System, Domestic Systems etc..) | 7 | 2026-08-06 | 2026-08-12
Test prior to handover to commissioning | 1